## Schedule
Production Line | Order | Material | Description | Batch ID | GCAS | System | Tank Config | Total MSU | Tech Type | Shift | Mkg Start Time | BCT (min) | Mkg End Time | Buffer (min) | Storage Tank | Pkg Start Time | Pkg End Time | MRP Status
INTERNAL | AUTO_1 | 95619314 | HC BASE | REP01-0112 | 95619314 | 12T | FMT+MMT | 2.2948 | Dual | A | 2026-01-11 09:00 | 90 | 2026-01-11 10:30 | 570 | HC Base Tank | 2026-01-11 20:00 | 2026-01-11 21:00 | LOW: SLS
INT2 | 910725376 + 910726630 | 80879278 | PTN Hair Fall Control | CI434 | 21302239 | 12T | FMT+MMT | 4.4891 | Dual | A | 2026-01-11 10:50 | 90 | 2026-01-11 12:20 | 636 | NO_TANK_AVAILABLE | 2026-01-11 22:56 | 2026-01-13 17:15 | LOW: SLS
INC1 | 910721946 | 83900263 | H&S Daily Clean Libra | CI435 | 21470269 | 12T | FMT | 4.4185 | Single | A | 2026-01-11 12:20 | 90 | 2026-01-11 13:50 | 730 | NO_TANK_AVAILABLE | 2026-01-12 02:00 | 2026-01-12 06:25 | LOW: SLS
INC1 | 910721918 | 83900263 | H&S Daily Clean Libra | CI436 | 21470269 | 12T | FMT | 4.4185 | Single | A | 2026-01-11 13:50 | 90 | 2026-01-11 15:20 | 905 | NO_TANK_AVAILABLE | 2026-01-12 06:25 | 2026-01-12 10:50 | LOW: SLS
INT2 | 910725305 + 910726648 | 80879281 | PTN Lively Clean | CI437 | 20256318 | 12T | FMT | 7.9415 | Single | B | 2026-01-11 15:40 | 90 | 2026-01-11 17:10 | 961 | NO_TANK_AVAILABLE | 2026-01-12 09:11 | 2026-01-13 14:22 | LOW: SLS
INC4 | 910721814 | 83900259 | H&S Daily Clean Libra | CI438 | 21470269 | 12T | FMT | 4.4163 | Single | B | 2026-01-11 17:10 | 90 | 2026-01-11 18:40 | 902 | NO_TANK_AVAILABLE | 2026-01-12 09:42 | 2026-01-12 14:50 | LOW: SLS
INC1 | 910721983 | 83900263 | H&S Daily Clean Libra | CI440 | 21470269 | 12T | FMT | 4.4185 | Single | B | 2026-01-11 18:40 | 90 | 2026-01-11 20:10 | 880 | NO_TANK_AVAILABLE | 2026-01-12 10:50 | 2026-01-12 15:14 | LOW: SLS
INC4 | 910722036 + 910721916 | 83900261 | H&S Daily Smooth Libra | CI443 | 21470270 | 12T | FMT | 4.4185 | Single | B | 2026-01-11 20:10 | 90 | 2026-01-11 21:40 | 1030 | NO_TANK_AVAILABLE | 2026-01-12 14:50 | 2026-01-12 19:57 | LOW: SLS
INTERNAL | AUTO_2 | 95619314 | HC BASE | REP02-0112 | 95619314 | 12T | FMT+MMT | 2.2948 | Dual | B | 2026-01-11 22:00 | 90 | 2026-01-11 23:30 | 960 | HC Base Tank | 2026-01-12 15:30 | 2026-01-12 16:30 | LOW: SLS
INT2 | 910725356 + 910725324 | 80880903 | H&S SS | CI444 | 21422079 | 12T | FMT | 5.2733 | Single | A | 2026-01-12 07:50 | 90 | 2026-01-12 09:20 | 382 | NO_TANK_AVAILABLE | 2026-01-12 15:42 | 2026-01-12 19:28 | LOW: SLS
INC1 | 910722019 | 83900263 | H&S Daily Clean Libra | CI445 | 21470269 | 12T | FMT | 4.4185 | Single | A | 2026-01-12 09:20 | 90 | 2026-01-12 10:50 | 340 | NO_TANK_AVAILABLE | 2026-01-12 16:30 | 2026-01-12 20:54 | LOW: SLS
INC1 | 910726422 | 83900263 | H&S Daily Clean Libra | CI448 | 21470269 | 12T | FMT | 4.4185 | Single | A | 2026-01-12 10:50 | 90 | 2026-01-12 12:20 | 514 | NO_TANK_AVAILABLE | 2026-01-12 20:54 | 2026-01-13 01:19 | LOW: SLS
INC4 | 910726423 | 83900262 | H&S Daily Cool Libra | CI451 | 21453170 | 12T | FMT | 4.4163 | Single | A | 2026-01-12 12:20 | 90 | 2026-01-12 13:50 | 521 | NO_TANK_AVAILABLE | 2026-01-12 22:31 | 2026-01-13 03:39 | LOW: SLS
INC1 | 910726577 | 83900263 | H&S Daily Clean Libra | CI452 | 21470269 | 12T | FMT | 4.4185 | Single | A | 2026-01-12 13:50 | 90 | 2026-01-12 15:20 | 599 | NO_TANK_AVAILABLE | 2026-01-13 01:19 | 2026-01-13 05:43 | LOW: SLS
INC4 | 910726576 | 83900262 | H&S Daily Cool Libra | CI453 | 21453170 | 12T | FMT | 4.4163 | Single | A | 2026-01-12 15:20 | 90 | 2026-01-12 16:50 | 649 | NO_TANK_AVAILABLE | 2026-01-13 03:39 | 2026-01-13 08:46 | LOW: SLS
INC1 | 910726538 | 83900263 | H&S Daily Clean Libra | CI454 | 21470269 | 12T | FMT | 4.4185 | Single | B | 2026-01-12 16:50 | 90 | 2026-01-12 18:20 | 683 | NO_TANK_AVAILABLE | 2026-01-13 05:43 | 2026-01-13 10:08 | LOW: SLS
INC4 | 910726596 | 83900262 | H&S Daily Cool Libra | CI456 | 21453170 | 12T | FMT | 4.4163 | Single | B | 2026-01-12 18:20 | 90 | 2026-01-12 19:50 | 776 | NO_TANK_AVAILABLE | 2026-01-13 08:46 | 2026-01-13 14:33 | LOW: SLS
INTERNAL | AUTO_3 | 95619314 | HC BASE | REP03-0112 | 95619314 | 12T | FMT+MMT | 2.2948 | Dual | B | 2026-01-12 20:10 | 90 | 2026-01-12 21:40 | 722 | HC Base Tank | 2026-01-13 09:42 | 2026-01-13 10:42 | LOW: SLS
INC1 | 910726537 | 83900263 | H&S Daily Clean Libra | CI457 | 21470269 | 12T | FMT | 4.4185 | Single | B | 2026-01-12 22:00 | 90 | 2026-01-12 23:30 | 638 | NO_TANK_AVAILABLE | 2026-01-13 10:08 | 2026-01-13 15:12 | LOW: SLS
INT2 | 910726631 | 80879271 | PTN Silky Smooth Shampoo | CI458 | '21302240 | 12T | FMT+MMT | 2.9398 | Dual | A | 2026-01-13 08:22 | 90 | 2026-01-13 09:52 | 270 | NO_TANK_AVAILABLE | 2026-01-13 14:22 | 2026-01-13 15:49 | LOW: SLS
INC4 | 910726493 | 83900260 | H&S Daily Cool Libra | CI459 | 21453170 | 12T | FMT | 4.4185 | Single | A | 2026-01-13 10:12 | 90 | 2026-01-13 11:42 | 171 | NO_TANK_AVAILABLE | 2026-01-13 14:33 | 2026-01-13 19:41 | LOW: SLS
INC1 | 910726509 | 83900263 | H&S Daily Clean Libra | CI460 | 21470269 | 12T | FMT | 4.4185 | Single | A | 2026-01-13 11:42 | 90 | 2026-01-13 13:12 | 120 | NO_TANK_AVAILABLE | 2026-01-13 15:12 | 2026-01-13 19:37 | LOW: SLS
INT2 | 910726541 | 80880902 | H&S SS | CI461 | 21422079 | 12T | FMT | 4.5228 | Single | A | 2026-01-13 13:45 | 90 | 2026-01-13 15:15 | 120 | NO_TANK_AVAILABLE | 2026-01-13 17:15 | 2026-01-13 20:08 | LOW: SLS
INC4 | 910726494 | 83900260 | H&S Daily Cool Libra | CI462 | 21453170 | 12T | FMT | 4.4185 | Single | B | 2026-01-13 16:11 | 90 | 2026-01-13 17:41 | 120 | NO_TANK_AVAILABLE | 2026-01-13 19:41 | 2026-01-14 00:49 | LOW: SLS
INT3 | 910722385 + 910722300 | 80841060 | PTN SS Conditioner | CI433 | 21090112 | 6T | FMT+MMT | 1.1202 | Dual | A | 2026-01-10 08:31 | 90 | 2026-01-10 10:01 | 1440 | NO_TANK_AVAILABLE | 2026-01-11 10:01 | 2026-01-12 10:23 | OK
INT3 | 910722223 | 80851521 | PTN SS Conditioner | CI439 | 21090112 | 6T | FMT+MMT | 0.28 | Dual | A | 2026-01-10 11:31 | 90 | 2026-01-10 13:01 | 2722 | NO_TANK_AVAILABLE | 2026-01-12 10:23 | 2026-01-12 14:20 | OK
INT2 | 910725378 | 80880880 | H&S Deep Cleanse | CI441 | 21433484 | 6T | FMT | 2.2544 | Single | A | 2026-01-10 14:01 | 90 | 2026-01-10 15:31 | 2619 | NO_TANK_AVAILABLE | 2026-01-12 11:10 | 2026-01-12 13:26 | LOW: SLS
INT2 | 910725203 | 80878142 | H&S NEEM | CI442 | 91305780 | 6T | FMT | 2.2544 | Single | B | 2026-01-10 15:51 | 90 | 2026-01-10 17:21 | 2645 | NO_TANK_AVAILABLE | 2026-01-12 13:26 | 2026-01-12 15:42 | LOW: SLS
INT2 | 910725202 | 80880910 | H&S AHF | CI446 | 21417344 | 6T | FMT | 2.2511 | Single | B | 2026-01-10 17:58 | 90 | 2026-01-10 19:28 | 2880 | NO_TANK_AVAILABLE | 2026-01-12 19:28 | 2026-01-12 20:55 | LOW: SLS
INC4 | 910726421 | 83900207 | H&S Daily Smooth Libra | CI447 | 21470270 | 6T | FMT | 2.2082 | Single | B | 2026-01-10 19:48 | 90 | 2026-01-10 21:18 | 2799 | NO_TANK_AVAILABLE | 2026-01-12 19:57 | 2026-01-12 22:31 | LOW: SLS
INT2 | 910725088 | 80880899 | H&S SB | CI449 | 21422081 | 6T | FMT | 2.2511 | Single | B | 2026-01-10 21:38 | 90 | 2026-01-10 23:08 | 2747 | NO_TANK_AVAILABLE | 2026-01-12 20:55 | 2026-01-12 22:22 | LOW: SLS
INT2 | 910726667 | 80895913 | H&S CM 2in1 | CI450 | 21422088 | 6T | FMT | 2.2511 | Single | B | 2026-01-10 23:28 | 90 | 2026-01-11 00:58 | 2724 | NO_TANK_AVAILABLE | 2026-01-12 22:22 | 2026-01-13 07:48 | LOW: SLS
INT2 | 910726580 | 80895916 | H&S AHF 2in1 | CI455 | 21412529 | 6T | FMT | 2.2511 | Single | C | 2026-01-11 06:18 | 90 | 2026-01-11 07:48 | 2880 | NO_TANK_AVAILABLE | 2026-01-13 07:48 | 2026-01-13 09:15 | LOW: SLS

## System Timeline
Time | Shift | 12T | 6T | 1.25T
2026-01-10 08:00 | A
2026-01-10 08:30 | A
2026-01-10 09:00 | A |  | CI433: PTN SS Conditioner
2026-01-10 09:30 | A |  | CI433: PTN SS Conditioner
2026-01-10 10:00 | A |  | CI433: PTN SS Conditioner
2026-01-10 10:30 | A |  | COND WASH (60m)
2026-01-10 11:00 | A |  | COND WASH (60m)
2026-01-10 11:30 | A
2026-01-10 12:00 | A |  | CI439: PTN SS Conditioner
2026-01-10 12:30 | A |  | CI439: PTN SS Conditioner
2026-01-10 13:00 | A |  | CI439: PTN SS Conditioner
2026-01-10 13:30 | A |  | COND WASH (60m)
2026-01-10 14:00 | A |  | COND WASH (60m)
2026-01-10 14:30 | A |  | CI441: H&S Deep Cleanse
2026-01-10 15:00 | A |  | CI441: H&S Deep Cleanse
2026-01-10 15:30 | B |  | CI441: H&S Deep Cleanse
2026-01-10 16:00 | B |  | CI442: H&S NEEM
2026-01-10 16:30 | B |  | CI442: H&S NEEM
2026-01-10 17:00 | B |  | CI442: H&S NEEM
2026-01-10 17:30 | B |  | WASHOUT
2026-01-10 18:00 | B |  | CI446: H&S AHF
2026-01-10 18:30 | B |  | CI446: H&S AHF
2026-01-10 19:00 | B |  | CI446: H&S AHF
2026-01-10 19:30 | B |  | WASHOUT
2026-01-10 20:00 | B |  | CI447: H&S Daily Smooth Libra
2026-01-10 20:30 | B |  | CI447: H&S Daily Smooth Libra
2026-01-10 21:00 | B |  | CI447: H&S Daily Smooth Libra
2026-01-10 21:30 | B |  | WASHOUT
2026-01-10 22:00 | B |  | CI449: H&S SB
2026-01-10 22:30 | B |  | CI449: H&S SB
2026-01-10 23:00 | B |  | CI449: H&S SB
2026-01-10 23:30 | C |  | CI450: H&S CM 2in1
2026-01-11 00:00 | C |  | CI450: H&S CM 2in1
2026-01-11 00:30 | C |  | CI450: H&S CM 2in1
2026-01-11 01:00 | C |  | WASHOUT
2026-01-11 01:30 | C
2026-01-11 02:00 | C
2026-01-11 02:30 | C
2026-01-11 03:00 | C
2026-01-11 03:30 | C
2026-01-11 04:00 | C
2026-01-11 04:30 | C
2026-01-11 05:00 | C
2026-01-11 05:30 | C
2026-01-11 06:00 | C
2026-01-11 06:30 | C |  | CI455: H&S AHF 2in1
2026-01-11 07:00 | C |  | CI455: H&S AHF 2in1
2026-01-11 07:30 | A |  | CI455: H&S AHF 2in1
2026-01-11 08:00 | A
2026-01-11 08:30 | A
2026-01-11 09:00 | A | REP01-0112: HC BASE
2026-01-11 09:30 | A | REP01-0112: HC BASE
2026-01-11 10:00 | A | REP01-0112: HC BASE
2026-01-11 10:30 | A | WASHOUT
2026-01-11 11:00 | A | CI434: PTN Hair Fall Control
2026-01-11 11:30 | A | CI434: PTN Hair Fall Control
2026-01-11 12:00 | A | CI434: PTN Hair Fall Control
2026-01-11 12:30 | A | CI435: H&S Daily Clean Libra
2026-01-11 13:00 | A | CI435: H&S Daily Clean Libra
2026-01-11 13:30 | A | CI435: H&S Daily Clean Libra
2026-01-11 14:00 | A | CI436: H&S Daily Clean Libra
2026-01-11 14:30 | A | CI436: H&S Daily Clean Libra
2026-01-11 15:00 | A | CI436: H&S Daily Clean Libra
2026-01-11 15:30 | B | WASHOUT
2026-01-11 16:00 | B | CI437: PTN Lively Clean
2026-01-11 16:30 | B | CI437: PTN Lively Clean
2026-01-11 17:00 | B | CI437: PTN Lively Clean
2026-01-11 17:30 | B | CI438: H&S Daily Clean Libra
2026-01-11 18:00 | B | CI438: H&S Daily Clean Libra
2026-01-11 18:30 | B | CI438: H&S Daily Clean Libra
2026-01-11 19:00 | B | CI440: H&S Daily Clean Libra
2026-01-11 19:30 | B | CI440: H&S Daily Clean Libra
2026-01-11 20:00 | B | CI440: H&S Daily Clean Libra
2026-01-11 20:30 | B | CI443: H&S Daily Smooth Libra
2026-01-11 21:00 | B | CI443: H&S Daily Smooth Libra
2026-01-11 21:30 | B | CI443: H&S Daily Smooth Libra
2026-01-11 22:00 | B | REP02-0112: HC BASE
2026-01-11 22:30 | B | REP02-0112: HC BASE
2026-01-11 23:00 | B | REP02-0112: HC BASE
2026-01-11 23:30 | C | WASHOUT
2026-01-12 00:00 | C
2026-01-12 00:30 | C
2026-01-12 01:00 | C
2026-01-12 01:30 | C
2026-01-12 02:00 | C
2026-01-12 02:30 | C
2026-01-12 03:00 | C
2026-01-12 03:30 | C
2026-01-12 04:00 | C
2026-01-12 04:30 | C
2026-01-12 05:00 | C
2026-01-12 05:30 | C
2026-01-12 06:00 | C
2026-01-12 06:30 | C
2026-01-12 07:00 | C
2026-01-12 07:30 | A
2026-01-12 08:00 | A | CI444: H&S SS
2026-01-12 08:30 | A | CI444: H&S SS
2026-01-12 09:00 | A | CI444: H&S SS
2026-01-12 09:30 | A | CI445: H&S Daily Clean Libra
2026-01-12 10:00 | A | CI445: H&S Daily Clean Libra
2026-01-12 10:30 | A | CI445: H&S Daily Clean Libra
2026-01-12 11:00 | A | CI448: H&S Daily Clean Libra
2026-01-12 11:30 | A | CI448: H&S Daily Clean Libra
2026-01-12 12:00 | A | CI448: H&S Daily Clean Libra
2026-01-12 12:30 | A | CI451: H&S Daily Cool Libra
2026-01-12 13:00 | A | CI451: H&S Daily Cool Libra
2026-01-12 13:30 | A | CI451: H&S Daily Cool Libra
2026-01-12 14:00 | A | CI452: H&S Daily Clean Libra
2026-01-12 14:30 | A | CI452: H&S Daily Clean Libra
2026-01-12 15:00 | A | CI452: H&S Daily Clean Libra
2026-01-12 15:30 | B | CI453: H&S Daily Cool Libra
2026-01-12 16:00 | B | CI453: H&S Daily Cool Libra
2026-01-12 16:30 | B | CI453: H&S Daily Cool Libra
2026-01-12 17:00 | B | CI454: H&S Daily Clean Libra
2026-01-12 17:30 | B | CI454: H&S Daily Clean Libra
2026-01-12 18:00 | B | CI454: H&S Daily Clean Libra
2026-01-12 18:30 | B | CI456: H&S Daily Cool Libra
2026-01-12 19:00 | B | CI456: H&S Daily Cool Libra
2026-01-12 19:30 | B | CI456: H&S Daily Cool Libra
2026-01-12 20:00 | B | WASHOUT
2026-01-12 20:30 | B | REP03-0112: HC BASE
2026-01-12 21:00 | B | REP03-0112: HC BASE
2026-01-12 21:30 | B | REP03-0112: HC BASE
2026-01-12 22:00 | B | CI457: H&S Daily Clean Libra
2026-01-12 22:30 | B | CI457: H&S Daily Clean Libra
2026-01-12 23:00 | B | CI457: H&S Daily Clean Libra
2026-01-12 23:30 | C | WASHOUT
2026-01-13 00:00 | C
2026-01-13 00:30 | C
2026-01-13 01:00 | C
2026-01-13 01:30 | C
2026-01-13 02:00 | C
2026-01-13 02:30 | C
2026-01-13 03:00 | C
2026-01-13 03:30 | C
2026-01-13 04:00 | C
2026-01-13 04:30 | C
2026-01-13 05:00 | C
2026-01-13 05:30 | C
2026-01-13 06:00 | C
2026-01-13 06:30 | C
2026-01-13 07:00 | C
2026-01-13 07:30 | A
2026-01-13 08:00 | A
2026-01-13 08:30 | A | CI458: PTN Silky Smooth Shampoo
2026-01-13 09:00 | A | CI458: PTN Silky Smooth Shampoo
2026-01-13 09:30 | A | CI458: PTN Silky Smooth Shampoo
2026-01-13 10:00 | A | WASHOUT
2026-01-13 10:30 | A | CI459: H&S Daily Cool Libra
2026-01-13 11:00 | A | CI459: H&S Daily Cool Libra
2026-01-13 11:30 | A | CI459: H&S Daily Cool Libra
2026-01-13 12:00 | A | CI460: H&S Daily Clean Libra
2026-01-13 12:30 | A | CI460: H&S Daily Clean Libra
2026-01-13 13:00 | A | CI460: H&S Daily Clean Libra
2026-01-13 13:30 | A
2026-01-13 14:00 | A | CI461: H&S SS
2026-01-13 14:30 | A | CI461: H&S SS
2026-01-13 15:00 | A | CI461: H&S SS
2026-01-13 15:30 | B
2026-01-13 16:00 | B
2026-01-13 16:30 | B | CI462: H&S Daily Cool Libra
2026-01-13 17:00 | B | CI462: H&S Daily Cool Libra
2026-01-13 17:30 | B | CI462: H&S Daily Cool Libra
2026-01-13 18:00 | B
2026-01-13 18:30 | B
2026-01-13 19:00 | B

## BPR-PDR
Sr.No | Date | Batch No | FC GCAS | Bulk Description | Line | Mkg System | Issued By Date/Sign/ Time | Issued To Date/Sign/ Time | P Code
1 | 11-Jan-26 | REP01-0112 | 95619314 | HC BASE | INTERNAL | 12T |  |  | 95619314
2 | 11-Jan-26 | CI434 | 21302239 | PTN Hair Fall Control | INT2 | 12T |  |  | 80879278
3 | 11-Jan-26 | CI435 | 21470269 | H&S Daily Clean Libra | INC1 | 12T |  |  | 83900263
4 | 11-Jan-26 | CI436 | 21470269 | H&S Daily Clean Libra | INC1 | 12T |  |  | 83900263
5 | 11-Jan-26 | CI437 | 20256318 | PTN Lively Clean | INT2 | 12T |  |  | 80879281
6 | 11-Jan-26 | CI438 | 21470269 | H&S Daily Clean Libra | INC4 | 12T |  |  | 83900259
7 | 11-Jan-26 | CI440 | 21470269 | H&S Daily Clean Libra | INC1 | 12T |  |  | 83900263
8 | 11-Jan-26 | CI443 | 21470270 | H&S Daily Smooth Libra | INC4 | 12T |  |  | 83900261
9 | 11-Jan-26 | REP02-0112 | 95619314 | HC BASE | INTERNAL | 12T |  |  | 95619314
10 | 12-Jan-26 | CI444 | 21422079 | H&S SS | INT2 | 12T |  |  | 80880903
11 | 12-Jan-26 | CI445 | 21470269 | H&S Daily Clean Libra | INC1 | 12T |  |  | 83900263
12 | 12-Jan-26 | CI448 | 21470269 | H&S Daily Clean Libra | INC1 | 12T |  |  | 83900263
13 | 12-Jan-26 | CI451 | 21453170 | H&S Daily Cool Libra | INC4 | 12T |  |  | 83900262
14 | 12-Jan-26 | CI452 | 21470269 | H&S Daily Clean Libra | INC1 | 12T |  |  | 83900263
15 | 12-Jan-26 | CI453 | 21453170 | H&S Daily Cool Libra | INC4 | 12T |  |  | 83900262
16 | 12-Jan-26 | CI454 | 21470269 | H&S Daily Clean Libra | INC1 | 12T |  |  | 83900263
17 | 12-Jan-26 | CI456 | 21453170 | H&S Daily Cool Libra | INC4 | 12T |  |  | 83900262
18 | 12-Jan-26 | REP03-0112 | 95619314 | HC BASE | INTERNAL | 12T |  |  | 95619314
19 | 12-Jan-26 | CI457 | 21470269 | H&S Daily Clean Libra | INC1 | 12T |  |  | 83900263
20 | 13-Jan-26 | CI458 | '21302240 | PTN Silky Smooth Shampoo | INT2 | 12T |  |  | 80879271
21 | 13-Jan-26 | CI459 | 21453170 | H&S Daily Cool Libra | INC4 | 12T |  |  | 83900260
22 | 13-Jan-26 | CI460 | 21470269 | H&S Daily Clean Libra | INC1 | 12T |  |  | 83900263
23 | 13-Jan-26 | CI461 | 21422079 | H&S SS | INT2 | 12T |  |  | 80880902
24 | 13-Jan-26 | CI462 | 21453170 | H&S Daily Cool Libra | INC4 | 12T |  |  | 83900260
25 | 10-Jan-26 | CI433 | 21090112 | PTN SS Conditioner | INT3 | 6T |  |  | 80841060
26 | 10-Jan-26 | CI439 | 21090112 | PTN SS Conditioner | INT3 | 6T |  |  | 80851521
27 | 10-Jan-26 | CI441 | 21433484 | H&S Deep Cleanse | INT2 | 6T |  |  | 80880880
28 | 10-Jan-26 | CI442 | 91305780 | H&S NEEM | INT2 | 6T |  |  | 80878142
29 | 10-Jan-26 | CI446 | 21417344 | H&S AHF | INT2 | 6T |  |  | 80880910
30 | 10-Jan-26 | CI447 | 21470270 | H&S Daily Smooth Libra | INC4 | 6T |  |  | 83900207
31 | 10-Jan-26 | CI449 | 21422081 | H&S SB | INT2 | 6T |  |  | 80880899
32 | 10-Jan-26 | CI450 | 21422088 | H&S CM 2in1 | INT2 | 6T |  |  | 80895913
33 | 11-Jan-26 | CI455 | 21412529 | H&S AHF 2in1 | INT2 | 6T |  |  | 80895916